## Work Breakdown Structure
|  |  |  | Defining Phase |  |  |  | Design Phase | [9 empty] | Implementation and Testing |  |  | Producing Documentation |  |  |  | Creating Demo
|  | Define Resources |  |  | Define Schedule | User Experience Design | User Interface Design |  |  | Database Design |  |  |  | UML Diagram |  |  | Implementing Database | Implementing Client Side | Implementing Server Side | Document and report test results |  | Technical Documentation | Choose Role | Choose Location | Choose Schedule | Make Raw Video | Edit Video
| Define Tools |  | Define Human Resources |  |  | Screen Flow Diagram | Design Prototype |  | ERD |  | Normalization | Class Diagram | Usecase Diagram |  | Sequence Diagram | Activity Diagram | Test Implemented codes | Test Implemented codes | Test Implemented codes | Proofreading |  | Proofreading |  |  |  |  | Choose BGM
Define Software | Define Hardware |  |  |  |  | Design Prototype | Modify Unsatisfied Parts |  |  |  | Data Dictionary | Data Description | Usecase Description |  |  |  | Debugging and handling errors | Debugging and handling errors | Debugging and handling errors
Modify Unsatisfied Parts

## Predecessor Table
No | Task | Duration (Day(s)) | Predessor
A | Define Resources | 3 | Start
B | Define Schedule | 2 | Start
C | User Experience Design | 7 | A+B
D | User Interface Design | 15 | C
E | Database Design | 13 | A+B
F | UML Diagram | 20 | A+B
G | Implementing Database | 18 | E
H | Implementing Client Side | 20 | D+F
I | Implementing Server Side | 27 | D+F
J | Document and report test results | 25 | G+H+I
K | Technical Documentation | 15 | G+H+I
L | Choose Role | 2 | J+K
M | Choose Location | 3 | J+K
N | Choose Schedule | 2 | J+K
O | Make Raw Video | 20 | L+M+N
P | Edit Video | 14 | O
Critical Path - Start,A,C,D,I,J,M,O,P, End

## Resource Table
No | Task | Duration (Day(s)) | Predessor | Resources
A | Define Resources | 3 | Start | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | *
B | Define Schedule | 2 | Start | Nanda Aung
C | User Experience Design | 7 | A+B | Arkar Min Khant | *
D | User Interface Design | 15 | C | Arkar Min Khant | *
E | Database Design | 13 | A+B | Nanda Aung
F | UML Diagram | 20 | A+B | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel
G | Implementing Database | 18 | E | Nanda Aung
H | Implementing Client Side | 20 | D+F | Sie Thu Ko, Thet Paing Oo, Arkar Min Khant
I | Implementing Server Side | 27 | D+F | Thet Maung Maung Toe, Mya Thet Chel | *
J | Document and report test results | 25 | G+H+I | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | * | Critical Path - Start,A,C,D,I,J,M,O,P, End
K | Technical Documentation | 15 | G+H+I | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel
L | Choose Role | 2 | J+K | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel
M | Choose Location | 3 | J+K | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | *
N | Choose Schedule | 2 | J+K | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel
O | Make Raw Video | 20 | L+M+N | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | *
P | Edit Video | 14 | O | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | *
Critical Path - Start,A,C,D,I,J,M,O,P, End

## Resource Leveling
A | 6 | 6 | 6
C |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
D | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
I | [25 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
J | [52 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
M | [77 empty] | 6 | 6 | 6
O | [80 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
P | [100 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
B | 1 | 1
E |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
H | [25 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
K | [52 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
L | [77 empty] | 6 | 6
N | [77 empty] | 6 | 6
| 7 | 7 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 18 | 18 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
18
17
16
15
14
13
12
11
10
9
8
7
6
5
4
3
2
1
A | 6 | 6 | 6
C |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
D | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
I | [25 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
J | [52 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
M | [77 empty] | 6 | 6 | 6
O | [80 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
P | [100 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
B | 1 | 1
E | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G | [34 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
H | [32 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
K | [54 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
L | [77 empty] | 6 | 6
N | [78 empty] | 6 | 6
| 7 | 7 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 12 | 18 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
18
17
16
15
14
13
12
11
10
9
8
7
6
5
4
3
2
1